## Sheet1
# | Task | Category | Status | Proposed Date for Resolution / SW Version | Additional Comments
1 | Thorough testing of permutations in table below* | Validation / Bug | Done* | 1.5.5 | Finished testing the various trace combinations, but I couldn't reproduce the intermittent error when plotting vs Pout. I did fix an issue you saw when moving from one X-axis type to another (say Pin to Frequency, and vice versa). Unfortunately the fix for now is for me to delete then recreate the trace entirely. I expect this will only need to be done when configuring the setup initially, so it shouldn't be a huge issue.
2 | Increase the number of points in power interpolation plots | Bug | Done |  | vs Pin, Pout plot points are x10
3 | End of sweep conditions (RF Off with power displayed at the bottom of plots) | Bug | In Progress* |  | This depends on a development team in Munich. I can make the request, but I don't know if/when it would get implemented. A work-around Greg recommended is to display the power range in the diagram title. Not sure if that would work. Another idea is to use markers to display the ranges.
4 | Move plots to a different figure | Bug | Done |  | Unfortunately, I had to reenable the data traces for the firmware to allow you to move the memory trace correctly
5 | Allow plot of gain and power values on the same figure | Bug | Done |  | You may have run into either the problem above, or the limitation of at most 20 traces per diagram (which includes data traces). I was able to do this.
6 | Resolve the scaling issue caused by a change in measurement conditions | Bug | In Progress* |  | I was able to reproduce and document this phenomenon. Unfortunately, it is an issue with our VNA firmware. I generated a report to send to our firmware developers. I will update you when I get a response, and I will continue to think of a work-around in the meantime.
7 | Message when plot of value exceeding the measurement boundaries | Improvement |  |  | A message is generated, and the value is rounded to the nearest valid value.
8 | Change plot nomenclature to something clearer (ie S11, S21, S12, S22) | Improvement | Done
9 | CSV file comma-delimeter | Improvement | Done
10 | CSV file add settings as header (combine previous files into CSV) | Improvement | In Progress
11 | CSV file add pulse definition info | Improvement | In Progress
12 | CSV file add phase of Pout (same as phase of S21) | Improvement | Done
13 | "Autoscale All" functionality | Improvement | Not started
14 | Minimized GUI | Improvement | In progress |  | On hold for critical bug fixes.
15 | Speed optimization | Improvement | In progress |  | On hold for critical bug fixes.
16 | Write a user manual for the application | Deliverable | Not started
*