## Sheet1
# | Task | Category | Status | Proposed Date for Resolution / SW Version | Additional Comments
1 | Thorough testing of permutations in table below* | Validation / Bug | Done* | 1.5.5* | Finished testing the various trace combinations, but I couldn't reproduce the intermittent error when plotting vs Pout. I did fix an issue you saw when moving from one X-axis type to another (say Pin to Frequency, and vice versa). Unfortunately the fix for now is for me to delete then recreate the trace entirely. I expect these trace changes will only need to be done during the initial configuration, so hopefully this isn't a big issue.
2 | Increase the number of points in power interpolation plots | Bug | Done | 1.5.5 | vs Pin, Pout plots have 10x points
3 | End of sweep conditions (RF Off with power displayed at the bottom of plots) | Bug | In Progress* |  | This depends on the development team in Munich. I can make the request, but I don't know if/when it would get implemented. A work-around Greg recommended is to display the power range in the diagram title. Not sure if that would work since in general the ranges in the diagram may not all be the same. Another idea is to use markers at the trace endpoints.
4 | Move plots to a different figure | Bug | Done | 1.5.5 | Unfortunately, I had to reenable the data traces for the firmware to allow you to move the memory trace correctly
5 | Allow plot of gain and power values on the same figure | Bug | Done | 1.5.5 | You may have run into either the problem above, or the limitation of at most 20 traces per diagram (which includes data traces). I was able to do this.
6 | Resolve the x-axis scaling issue caused by a change in measurement conditions | Bug | In Progress* |  | I was able to reproduce and document this phenomenon. Unfortunately, it is an issue with our VNA firmware. I generated a report to send to our firmware developers. I will update you when I get a response. A work-around would be for me to delete then recreate the trace entirely, but this would mean that you'd have to re-setup the plots (not convenient).
7 | Message when plot of value exceeding the measurement boundaries | Improvement | Not started | 1.5.6 | The GUI will not let you input incorrect values: any at value that is not possible is rounded to the nearest possible value. If you watch the value as you enter it, you should see this. That said, I will add a warning in the next version.
8 | Change plot nomenclature to something clearer (ie S11, S21, S12, S22) | Improvement | Done | 1.5.5
9 | CSV file comma-delimeter | Improvement | Done | 1.5.5
10 | CSV file add settings as header (combine previous files into CSV) | Improvement | In Progress | 1.5.6
11 | CSV file add pulse definition info | Improvement | In Progress | 1.5.6
12 | CSV file add phase of Pout (same as phase of S21) | Improvement | Done | 1.5.5 | FWIW, also added phase of Pin (0 deg)
13 | "Autoscale All" functionality | Improvement | Not started
14 | Minimized GUI | Improvement | In progress |  | On hold for critical bug fixes.
15 | Speed optimization | Improvement | In progress |  | On hold for critical bug fixes.
16 | Write a user manual for the application | Deliverable | Not started
*