## Ongoing
# | Task | Category | Status | SW Version | Date | Additional Comments | Jerome's Comment
1 | Capture DC voltage from an external DMM to calculate drain efficiency. | Improvement | Feasibility |  | 2017-03-17 | The ZVA needs to communicate with one or more Keysight 34465A DMM to measure current. Current is being read through the voltage drop in a small serial resistor on the bias line. User must be able to set the value of the resistor in the VNA to ensure proper current reading. Reading efficiency must be an option that can be enabled or disabled in order to keep measurement time low when it is uneeded. Efficiency is a parameter that can be plotted as a function of Pin, Pout and Frequency (X Parameter column). When Frequency is selected for X Parameter, Efficiency can be plotted at either fixed Pin or Pout, MaxGain or Compression.
2 | Define an arbitrary compression point for plot purpose. | Improvement | Not started |  | 2017-03-17 | When "Compression" is selected in the plot control table, enable the last column to allow user to enter a compression level. In the background, compute and plot data to this arbitrary compression level.
3 | Allow user to define a default folder where data is saved. | Improvement | Not started |  |  | This path will be saved in the config file (if there is such thing). When the user select the export data option, this is the default path to be used. It is also the path to be used for item number 4.
4 | Auto save the measurement in a temp file in the default folder. | Improvement | Not started |  |  | To prevent loss of data in case the software crashes or if the amplifier gets destroyed.
5 | Provide a field to add a “comment ” line to the output data file. | Improvement | Not started
6 | Provide the option of saving only the csv files in the output folder (not in .zip format). | Improvement | Not started |  |  | Output files could be named PA1_Comp.csv and PA1_Data.csv, for instance. Give the user the option of exporting whatever data file he wants.
7 | Give the option to plot S11, S21, S12, S22, AMPM and Efficiency parameters over frequency, at a defined Pout | Improvement | Not started |  |  | Current version allows to plot at either fixed Pin, MaxGain and Compression, but not at fixed Pout. Puts zeros in the datafile if data doesn't exist at compression or at desired Pout.
8 | Add dB(S11) and Efficiency @ MaxGain and Compression in the Compression.csv data file | Improvement | Not started
9 | Fix the AM/PM calculation glitch | Bug | Not started |  |  | AM /PM shows a glitch when Phase(S21) crossses 180 degrees.
10 | Update user manual for the application | Deliverable | Not started

## Other
# | Task | Category | Status | SW Version | Date | Additional Comments | Jerome's Comment
Opt | "Autoscale All" functionality | Improvement |  |  |  | Could still discuss making a separate app for this. Maybe put it on hold for now? | Jerome : Proposal is to address this item in a small separate application.
Opt | Create memory traces to keep track of previous plots | Improvement